## Sheet1
Meteoroid Ejecta of Lunar Secondaries Engineering Model (MELSEM) Milestone Schedule to DSNE Publication
Milestones | Start Date | End Date | Notes | Comments
Receive official NESC final report | 2021-09-15 | 2021-09-15 | Not yet received
Incorporate selected NESC suggestions in code | 2021-01-10 | 2021-12-01 | Major refactoring of code to include Monte Carlo statistics
Code check run through | 2021-12-01 | 2021-12-12 | Bjorkman, or Anne? | Need to check availability
Check updated environment with HVIT Bumper | 2021-12-13 | 2022-01-07 | Plan to have updated particle size distribution for BLEs | Need to check availability
Informal Discussion with Matney & Bjorkman | 2022-01-07 | 2022-01-14
HLS SERF/TURF -- informational | 2021-01-15 | 2021-01-22 |  | Slide showing which NESC suggestions we attacked
Add environment to DSNE rev J | 2022-01-18 | 2022-03-31 | In-text description, tables, figures, technical notes, etc. | CY22 Q1 end, end of March baselines - 10 weeks
NEITT/Gateway/xEVA/SLS presentation | 2022-02-01 | 2022-02-14 | A subset of listed audiences maybe sufficient
EV01 presentation | 2022-02-01 | 2022-02-14 | Requested by Glenn et al. | Same presentation as SERF/TURF