## Sheet1
Meteoroid Ejecta of Lunar Secondaries Engineering Model (MELSEM) Milestone Schedule to DSNE Publication
Milestones | Start Date | End Date | Notes | Comments
Receive official NESC final report | 2021-09-15 | 2021-09-15 | Not yet received
Incorporate selected NESC suggestions in code | 2021-01-10 | 2021-12-01 | Major refactoring of code to include Monte Carlo statistics
Code check run through | 2021-12-01 | 2021-12-12 | Bjorkman, or Anne? | Need to check availability
Check updated environment with HVIT Bumper | 2021-12-13 | 2022-01-07 | Plan to have updated particle size distribution for BLEs | Need to check availability
Informal Discussion with Matney & Bjorkman | 2022-01-07 | 2022-01-14
HLS SERF/TURF -- informational | 2021-01-15 | 2021-01-22 |  | Slide showing which NESC suggestions we attacked
Add environment to DSNE rev J | 2022-01-18 | 2022-03-31 | In-text description, tables, figures, technical notes, etc. | CY22 Q1 end, end of March baselines - 10 weeks
NEITT/Gateway/xEVA/SLS presentation | 2022-02-01 | 2022-02-14 | A subset of listed audiences maybe sufficient
EV01 presentation | 2022-02-01 | 2022-02-14 | Requested by Glenn et al. | Same presentation as SERF/TURF

## Sheet1 (2)
Lunar Meteoroid Ejecta Engineering Model Milestone Schedule to DSNE Publication
Milestones | Start Date | End Date | Notes | Comments
Receive official NESC final report | 2021-12-17 | 2022-03-07 | Original date to receive was 9/15/21 | "signed" copy received 3/7/22
Incorporate selected NESC suggestions in code | 2021-01-10 | 2022-03-21 | Major refactoring of code to include Monte Carlo statistics | Finishing ejecta size and angular distribution
Code check run through | 2021-12-08 | 2022-03-25 | Paul Bremner (ST13)
Ejecta size dist chat w/ Caleb | 2022-02-22 | 2022-02-22 | Pointed towards Singer et al 2013/2020 papers | Seems to affect crater scaling, HH11 -> R^3 fixed, Singer has R^b, where b depends on total mass ejected
NESC rec meeting with MEO | 2022-03-08 | 2022-03-08 | W/ Bill and Althea | Sensitivity study on NEO ang dist (MEM LO vs HI), also see Drolshagen et al 2017 on MEM to NEO turning point
Env Summary meeting with MEO | 2022-03-28 | 2022-04-01 | Meeting after Paul gives OK on code
Generate DSNE env for HVIT | 2022-03-25 | 2022-04-08 | Time includes any mods from MEO suggestions
Internal EV44 final check on DSNE env | 2022-04-11 | 2022-04-15 | Time includes any last mods from EV44 suggestions
Send updated environment with HVIT Bumper | 2022-04-18 | 2022-04-22 | Plan to have updated particle size distribution for BLEs | Jim Hyde contacted us 3/9/2022, send in form of Memo (Emily/Barry ok, then Adrean for cover letter)
Informal Discussion with Matney & Bjorkman | 2022-01-07 | 2022-01-14
Add environment to DSNE rev J | 2022-01-18 | 2022-03-31 | In-text description, tables, figures, technical notes, etc. | DSNE can't be unfrozen until after Artemis I launch, June 2022
HLS SERF/TURF -- informational | 2021-01-15 | 2021-01-22 |  | Slide showing which NESC suggestions we attacked
NEITT/Gateway/xEVA/SLS presentation | 2022-02-01 | 2022-02-14 | A subset of listed audiences maybe sufficient
EV01 presentation | 2022-02-01 | 2022-02-14 | Requested by Glenn et al. | Same presentation as SERF/TURF